## Sheet1
Who | Bug Description | AddWhen | Pr | Fix | FixWhen | Tested/Verified by | TestWhen | 2017-12-19 10:44
Kim | Add new record button | 2017-12-13 09:50 |  | Added | 2017-12-13 09:56
James | Prevent inadvertent overwrite of JTLS_Num | 2017-12-13 09:50 |  | disabled JTLS Num unless double-clicked to unlock | 2017-12-13 09:56
James | reinstate default locking of Closed jobs | 2017-12-13 09:50 |  | should be working | 2017-12-13 09:56
James | Add Duplicate Flag to form (until duplicates cleaned up) | 2017-12-13 09:50 |  | added | 2017-12-13 09:58
Kim | What is QtyInv ??? | 2017-12-13 09:59 |  | QtyInv cleared, to be set later | 2017-12-13 10:00 | James | 2017-12-13 10:00
Kim | Duplicates populated with duplicate POs as well | 2017-12-13 09:50 |  | Deleted several, hopefully all | 2017-12-13 10:33
Kim | Invoice UOP > dropdown | 2017-12-13 09:50 |  | done | 2017-12-13 10:44
Kim | Add Unmatched invoice query | 2017-12-13 11:18 | 5 |  | 2017-12-13 12:17
Kim | Display PO currency on invoice entry dropdowns | 2017-12-13 09:50 | 5 | added | 2017-12-13 12:18
Kim | invoice When drop down for POs not allowing changes | 2017-12-13 11:18 | 5 | fixed | 2017-12-13 12:18
Kim | Invoice button should pull up selected PO | 2017-12-13 10:16 | 9 | removed Invoice button | 2017-12-13 12:18
James | Add Search/Filter button for common fields | 2017-12-13 09:50 | 5 | added | 2017-12-13 12:29
Kim | Add Search buttons to JTLS# field and description | 2017-12-13 12:41 | 5 | added | 2017-12-13 12:29
Kim | Quotes button default to new quote. Dbl-click to specific quote. Add AL # to list. | 2017-12-13 13:33 | 1 | done, though dbl-click only takes to quotes for Job_Num | 2017-12-13 14:39
Kim | Change main form - Poto be at summary level not line level | 2017-12-13 14:48 |  | done | 2017-12-13 14:48
Di | New quote should default to Job_Num. UOM/CC dropdowns. UnitLab, UnitMat. | 2017-12-13 13:07 | 5 | done | 2017-12-13 15:49
James | Job List not updated after filter | 2017-12-13 12:42 | 5 | fixed | 2017-12-13 15:49
Kim | Quotes - quote no. is job no., quote line not reqd. Qty and UOM not reqd. Description is Quote Notes. | 2017-12-13 13:33 | 1 | one, except decided to leave QuoteLn active (eg for separating AUD and USD quote lines) | 2017-12-13 15:51
Di | Quotesent.oldvalue on new quote null causes debug, then when responsedays added response date didn't calculate (+30work days) | 2017-12-13 13:33 | 1 | fixed | 2017-12-13 16:12
Kim | refresh Jobs_frm after changes made in Quotes/POs/Invoices | 2017-12-13 09:50 | 5 | fixed | 2017-12-13 16:12
Kim | Add Search by PO | 2017-12-13 12:41 | 5 | added | 2017-12-13 16:46
Kim | Relock JTLS # | 2017-12-14 10:09 | 5 | resets value with warning if changes made | 2017-12-14 13:12
James | Job rec saves with cust blank | 2017-12-14 10:10 | 5 | applied Not Null validation | 2017-12-14 13:13
James | Prevent quote form being opened while Job not saved. | 2017-12-14 10:10 | 5 | fixed | 2017-12-14 13:15
Di | WBS not auto populating properly | 2017-12-14 10:31 | 5 | fixed by moving control to Job_num for new not dirty record | 2017-12-14 13:21
James | Requery upon popup close is causing record seletion on Jobs to revert to first rec | 2017-12-14 13:33 | 4 | changed requery to only affect quote or PO lists | 2017-12-15 10:09
Kim | When closing out of the quotes, jobs list always revert to the original entry (non al) | 2017-12-15 08:57 | 5 | fixed | 2017-12-15 10:09
James | Use QuoteNo/QuoteRef to tie PO lines to proper Quote (rather than just job) | 2017-12-13 09:57 | 5 | chgd QuoteNo to be JobNo.QuoteLn, updated db, added functionality to Quote form (incl. to allow chg to QuoteNo with any attached POs updated) | 2017-12-15 11:38
Kim | Quote status need to be moved to the Quote level and not on the records level | 2017-12-15 11:38 | 5 | added (is "Response" now redundant?") | 2017-12-15 11:42
Di | Extend the number of characters in the comments field | 2017-12-13 14:48 | 5 | chgd to Memo, allows mega-text but may not work for filtering/searching? | 2017-12-15 12:06
james | Quote double click not working | 2017-12-14 10:37 | 5 | fixed using Got/lost Focus, also for listPOs | 2017-12-15 12:13
Kim | Quotes - Add Quote Status, add new buttons. | 2017-12-13 13:33 | 2 | added | 2017-12-15 12:13
Kim | Quotes - Add Save&Close | 2017-12-13 13:33 | 2 | added | 2017-12-15 12:19
Kim | 0955 PO Total $32M incorrect! | 2017-12-14 12:53 | 3 | fixed! | 2017-12-15 12:13
Kim | Job list should only show open tasks when unfiltered - button to be added to show closed ones as well - "Show all Jobs" | 2017-12-14 10:09 | 4
Kim | Add Line value, Qty invoices and balance remaining to PO individual records | 2017-12-13 12:41 | 5
Kim | Add line level functionality to the PO form. | 2017-12-13 14:48 | 5
Kim | Double Click into PO (jtls01124) causes run time error 2113 | 2017-12-13 15:52 | 5
Kim | Trying to enter a quotation (1168) causes runtime error 424 after record is entered | 2017-12-13 15:52 | 5
Kim | Invoice on - Refer 1149 USD PO | 2017-12-13 12:41 | 6
Kim | Unable to add or revise existing record | 2017-12-14 10:09 | 6
Kim | Qty invoiced totals not working | 2017-12-13 12:41 | 9 | don't need QtyInv field?
James | check referential integrity/update for PO_Ln POs>Invoices | 2017-12-13 10:07 | 9 | can't do due to unmatched invoices
Kim | New Invoice details not populating correctly and hitting debug | 2017-12-13 09:50 | 9 | wrkg if dbl-click through form PO?
Kim | Have "Purchase Orders" open to the selected PO | 2017-12-18 10:44 |  | fixed | 2017-12-18 11:32